## Estimation Template
{HD}
HD Games
{Task Name} | Mentor | Yuxiang Huang | Xin Lin | Baiwei Liu | Wenlao Peng | Yitao Ma | Hang Yang | {Average Hour}
{MVF 1 - Login and Registration} | 10 | 2 | 25 | 2 | 4 | 4 | 2 | 7
{MVF 2 - Online Game} | 20 | 3 | 12 | 10 | 3 | 2 | 30 | 11.4286
{MVF 3 - Blog} | 15 | 11 | 5 | 30 | 2 | 2 | 3 | 9.7143
{MVF 4 - Purchase Products} | 25 | 27 | 5 | 3 | 2 | 2 | 3 | 9.5714
{MVF 5 - Ranking List} | 15 | 5 | 8 | 3 | 24 | 3 | 23 | 11.5714
{MVF List all others} | [7 empty] | 0
{MVF e.g 6 - Game Selling Page(Template)} | 10 | 3 | 3 | 2 | 4 | 24 | 3 | 7
{MVF e.g 7 - Insert title} | [7 empty] | 0
etc.. | [7 empty] | 0
{Extended Feature 1 - Contact Table} | 5 | 4 | 5 | 6 | 3 | 4 | 3 | 4.2857
{Extended Feature 2 - Search} | 5 | 3 | 3 | 2 | 4 | 2 | 4 | 3.2857
{Extended Feature 3 - Navigation} | 5 | 4 | 4 | 4 | 4 | 1 | 4 | 3.7143
All other Extended Features | [7 empty] | 0
{Extended Feature e.g 4 - Insert title} | [7 empty] | 0
{Extended Feature e.g 5 - Insert title} | [7 empty] | 0
{Extended Feature e.g 6 - Insert title} | [7 empty] | 0
etc.. | [7 empty] | 0
[7 empty] | Total: | 67.5714

## Yuxiang Huang
Member: Yuxiang Huang
MVF1: Login and Registration | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 0 | 0 | 1 | 2
MVF2: Online Game | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
MVF3: Blog | Learning | Research | Design | Coding | Testing | Total
| 3 | 3 | 3 | 1 | 1 | 11
MVF4: Purchase Products | Learning | Research | Design | Coding | Testing | Total
| 4 | 2 | 5 | 13 | 3 | 27
MVF5: Ranking List | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 1 | 1 | 5
MVF6: Game Selling Page(Template) | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 0 | 0 | 2 | 3
Extended Feature 1 - Contact Table | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 0 | 1 | 4
Extended Feature 2 - Search | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 1 | 0 | 3
Extended Feature 3 - Navigation | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 1 | 0 | 4

## Xin Lin
Member - Xin Lin
MVF1: Login and Registration | Learning | Research | Design | Coding | Testing | Total
| 5 | 5 | 3 | 7 | 5 | 25
MVF2: Online Game | Learning | Research | Design | Coding | Testing | Total
| 2 | 2 | 2 | 4 | 2 | 12
MVF3: Blog | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 1 | 1 | 5
MVF4: Purchase Products | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 1 | 1 | 5
MVF5: Ranking List | Learning | Research | Design | Coding | Testing | Total
| 1 | 2 | 1 | 3 | 1 | 8
MVF6: Game Selling Page(Template) | Learning | Research | Design | Coding | Testing | Total
| 0 | 0 | 1 | 1 | 1 | 3
Extended Feature 1 - Contact Table | Learning | Research | Design | Coding | Testing | Total
| 0 | 0 | 1 | 3 | 1 | 5
Extended Feature 2 - Search | Learning | Research | Design | Coding | Testing | Total
| 0 | 0 | 0 | 2 | 1 | 3
Extended Feature 3 - Navigation | Learning | Research | Design | Coding | Testing | Total
| 0 | 0 | 1 | 2 | 1 | 4

## Baiwei Liu
Member - Baiwei Liu
MVF1: Login and Registration | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 0 | 0 | 1 | 2
MVF2: Online Game | Learning | Research | Design | Coding | Testing | Total
| 3 | 2 | 2 | 2 | 1 | 10
MVF3: Blog | Learning | Research | Design | Coding | Testing | Total
| 6 | 5 | 8 | 8 | 3 | 30
MVF4: Purchase Products | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
MVF5: Ranking List | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
MVF6: Game Selling Page(Template) | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 0 | 0 | 1 | 2
Extended Feature 1 - Contact Table | Learning | Research | Design | Coding | Testing | Total
| 2 | 1 | 1 | 1 | 1 | 6
Extended Feature 2 - Search | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 0 | 0 | 1 | 2
Extended Feature 3 - Navigation | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 1 | 1 | 1 | 4

## Wenlao Peng
Member: Wenlao Peng
MVF1: Login and Registration | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 1 | 0 | 4
MVF2: Online Game | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
MVF3: Blog | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 0 | 2
MVF4: Purchase Products | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 0 | 2
MVF5: Ranking List | Learning | Research | Design | Coding | Testing | Total
| 7 | 5 | 4 | 4 | 4 | 24
MVF6: Game Selling Page(Template) | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 0 | 1 | 4
Extended Feature 1 - Contact Table | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 0 | 0 | 3
Extended Feature 2 - Search | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 0 | 1 | 4
Extended Feature 3 - Navigation | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 0 | 1 | 4

## YiTao Ma
Member: YiTao Ma
Learning:I think I need to spend three hours in learning. Although I have learned some language about making web pages, I think I will use more skills in developing web template stage, so I may learn other new knowledge. It will take time.
Research: I think I need to spend about 5 hours on research, because I need to search a lot of resources on the Internet and screen out the resources that are suitable for my function. Because I pursue high quality development, good resources are necessary.
Design: I think I need to spend about 7 hours on the design, because I have to consider what kind of color or layout is suitable for the website selling games, and it should be different from the website on the market, because as long as the design is good, it will save you a lot of time in the future programming.
Coding: I think I need to spend about 7 hours on programming. Although web programming doesn't need a lot of logic, it may need JavaScript, so it takes a lot of time to think about an algorithm / logic. What's more, the spacing of each plate or hyperlink also needs a certain amount of time to complete. And when you're done, if there's a bug or error, you'll spend more time fixing it.
Testing: I think it will take me about two hours to complete the testing. Compared with other allocation time is less, because to test the web page, you only need to open the browser. If you find any problem, you can return to your code file, and then refresh the page after the change to update the content you have changed. So it doesn't take a lot of time to test the web. Another reason is that I have spent a lot of time on design and coding, so there won't be too many problems
MVF1: Login and Registration | Learning | Research | Design | Coding | Testing (working or not) | Total
| 1 | 1 | 1 | 1 |  | 4
MVF2: Online Game | Learning | Research | Design | Coding | Testing (working or not) | Total
| 1 | 0 | 0 | 1 |  | 2
MVF3: Blog | Learning | Research | Design | Coding | Testing (working or not) | Total
| 0 | 0 | 1 | 1 |  | 2
MVF4: Purchase Products | Learning | Research | Design | Coding | Testing (working or not) | Total
| 0 | 1 | 0 | 1 |  | 2
MVF5: Ranking List | Learning | Research | Design | Coding | Testing (working or not) | Total
| 1 | 0 | 1 | 1 |  | 3
MVF6: Game Selling Page(Template) | Learning | Research | Design | Coding | Testing (working or not) | Total
| 3 | 5 | 7 | 7 | 2 | 24 | The sum number will match the 27 number above (red)
Extended Feature 1 - Contact Table | Learning | Research | Design | Coding | Testing (working or not) | Total
| 1 | 1 | 1 | 1 |  | 4
Extended Feature 2 - Search | Learning | Research | Design | Coding | Testing (working or not) | Total
| 1 |  |  | 1 |  | 2
Extended Feature 3 - Navigation | Learning | Research | Design | Coding | Testing (working or not) | Total
| 0 | 0 | 0 | 1 |  | 1

## Hang Yang
Member: Hang Yang
MVF1: Login and Registration | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 0 | 0 | 1 | 2
MVF2: Online Game | Learning | Research | Design | Coding | Testing | Total
| 5 | 7 | 5 | 8 | 5 | 30
MVF3: Blog | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
MVF4: Purchase Products | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
MVF5: Ranking List | Learning | Research | Design | Coding | Testing | Total
| 5 | 5 | 4 | 4 | 5 | 23
MVF6: Game Selling Page(Template) | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
Extended Feature 1 - Contact Table | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 0 | 0 | 1 | 3
Extended Feature 2 - Search | Learning | Research | Design | Coding | Testing | Total
| 1 | 1 | 1 | 0 | 1 | 4
Extended Feature 3 - Navigation | Learning | Research | Design | Coding | Testing | Total
| 1 | 0 | 1 | 1 | 1 | 4